## Sprint1 Backlog
User Story ID | User Story | Priority | Task ID | Task Description | Assignee | Status | Estimated Hours | Actual Hours | Sprint
USER001 | User can log in | HIGH | T001 | Create login page |  | In Progress | 8 | 5 | Sprint 1
USER002 | User can log in | HIGH | T002 | Backend authentication |  | In Progress | 11 |  | Sprint 1
USER003 | User can view dashboard | MEDIUM | T003 | Design dashboard UI |  | To Do | 12 |  | Sprint 1
USER004 | User can view dashboard | HIGH | T004 | Implement dashboard API |  | To Do | 7 |  | Sprint 1
USER005 | User can log out | MEDIUM | T005 | Add logout functionality |  | Done | 4 | 4 | Sprint 1

## Sprint2 Backlog
User Story ID | User Story | Priority | Task ID | Task Description | Assignee | Status | Estimated Hours | Actual Hours | Sprint
USER001 | User can log in | HIGH | T001 | Implement signup functionality |  | Done | 8 | 5 | Sprint 2
USER002 | User can log in | HIGH | T002 | Backend authentication |  | Done | 11 |  | Sprint 2
USER003 | User can view dashboard | MEDIUM | T003 | Design dashboard UI using Boostrap |  | In Progress | 12 |  | Sprint 2
USER004 | User can view dashboard | HIGH | T004 | Implement dashboard API |  | To Do | 7 |  | Sprint 2
USER005 | User can log out | MEDIUM | T005 | Add logout functionality |  | Done | 4 | 4 | Sprint 2
USER006

## Sprint Backlog
User Story ID | User Story | Priority | Task ID | Task Description | Assignee | Status | Estimated Hours | Actual Hours | Sprint
US001 | User can create an account | High | T001 | Design signup page | Shobhit | In Progress | 8 | 4 | Sprint 1
US001 | User can create an account | High | T002 | Implement signup functionality | Shobhit | To Do | 12 |  | Sprint 1
US002 | User can book a cab | High | T003 | Create booking form UI | kavya | To Do | 10 |  | Sprint 1
US002 | User can book a cab | High | T004 | Implement booking logic | kavya | To Do | 15 |  | Sprint 1
US003 | User can view booking history | Medium | T005 | Develop booking history page | Swati | To Do | 8 |  | Sprint 2
US003 | User receives booking confirmation notification | Medium | T006 | Integrate notification service | Swati | To Do | 6 |  | Sprint 2
US004 | Driver can accept bookings | High | T007 | Create driver booking interface | Kiran | To Do | 12 |  | Sprint 2
US005 | User can make payments | High | T008 | Implement payment gateway | Jevadarshini | To Do | 20 |  | Sprint 3
US006 | User can rate and review rides | Medium | T009 | Design rating and review system | vaishnavi | To Do | 10 |  | Sprint 3
US006 | Admin can manage users and drivers | Low | T010 | Develop admin dashboard | vaishnavi | To Do | 18 | 12 | Sprint 3

## Product Backlog
PRODUCT BACKLOG ID | PRIORITY | USER STORY ID | user stories | scrum team assigned | status | remark
sprint 1
1 | high | user001 | User Registration & Validation | Shobhit team | completed
2 | high | user002 | Car Search & Availabilty | Kavya team | completed
sprint 2
3 | high | user003 | Booking Management | Kiran team | completed
sprint 3
4 | high | user004 | Payment Processing | Jevadarshini team | completed
5 | high | user005 | Admin Function | Vaishnavi team | partially completed